MILESTONES & ROLES

# TEAM: The High Fivers

## Project Title: Extending StackOverflow Gamification using Social Media

Project Members:

* Alastair Beaumont (**AB**)  Tim Baker (**TB**)
* Richard Wagner (**RBW**)
* Arturo Reyes Lopez (Grad) (**AR**)
* Nitin Goyal (Grad) (**NG**)

The following milestones have been planned to work on:

|  |  |  |
| --- | --- | --- |
| **Date** | **Milestone** | **Responsible** |
| **WEEK 1**  **October 2nd -**  **October 9th** | ~~Brainstorming meeting to come with ideas~~ | **AB,TB,RBW,AR,NG** |
| ~~Literature review~~ | **AR,NG** |
| ~~Write Initial Proposal~~ | **AB,TB,RBW,AR,NG** |
| ~~Improve the Proposal if needed after getting reviewed by Peggy~~ | **AB,TB,RBW,AR,NG** |
| **WEEK 2**  **October 12th -**  **October 16th** | ~~Writing proposal~~ | **AB, TB, RBW, AR, NG** |
| ~~Introduction~~ | **TB** |
| ~~Literature review~~ | **RBW, AR, NG** |
| ~~Expected Results~~ | **AB** |
| ~~Methodology, Research Questions, Design and Literature Review~~ | **AR, NG** |
| ~~Prepare slides for in class presentation proposal~~ | **AR,NG,TB** |
| ~~In class presentation~~ | **AB,RBW** |
| ~~Answering Feedback~~ | **RBW, AR, NG** |
| ~~Prepare final writing proposal for submission~~ | **AR, NG** |
| **WEEK 3**  **October 19th -**  **October 23rd** | Complete Ethics application and Consent form. | **AR, NG** |
| Define levels of reputation to study. | **RBW, AB** |
| Collect 150 users information by each defined category: high, medium and low reputation. | **RBW, AB** |
| Design questions for interviews (20 minutes duration). | **TB, NG, AR, RBW, AB** |
| Design questions for Survey. | **TB, NG, AR, RBW, AB** |
| Send emails to all participants in the research asking for permission to participate and explaining the research. | **AR,NG** |
| **WEEK 4**  **October 26th -**  **October 30th** | Apply survey questionnaires to UVic students in the CSCW class and StackOverflow members selected by reputation level (high, medium and low). | **TB,AB** |
| Transcript interviews and divide by theme. | **RBW, AR, NG** |
|  | Based on survey answers, include specific questions if it would be needed. | **AR, NG** |
| **WEEK 5**  **November 2nd - November 6th** | Apply interviews to StackOverflow members selected by reputation level (high, medium and low) through Skype | **NG, AR** |
| Apply interviews to UVic students in the CSCW class | **TB,AB,RBW** |
| Collect information to obtain quantitative  data (Graphs, measurements) | **TB, RBW, AB** |
| Design the user interface proposal to be shared on social media. What are the elements to be included? How will the UI look like? | **TB, AB, RBW** |
| **WEEK6**  **November 9th – November 13rd** | Include the gathered information to the interim project report (Progress) | **AB,TB,RW** |
| Meeting with Dr. Margaret-Anne Storey to check individual work on the project, general progress and feedback.. | **AB,TB,RW,AR,NG** |
| **WEEK 7**  **November 9th – November 13rd** | |  |  | | --- | --- | | Work on recommendations from the | | | interim project resented |  | | **NG, AR** |
| **WEEK 8**  **November 23rd – November 27th** | Writing final project report | **AB,TB,RW,AR,NG** |
| **WEEK 9**  **November 30th – December 6th** | Preparing Final Presentation | **NG, AR** |
| Improving Final project report | **AB,TB,RW,AR,NG** |