## Week 1
Project Diary (Log Book)
Team: The High Fivers
CSCW Project - Fall2015
Week 1 (28th Sept – 2nd October)
| Tasks | Hours Spent
Nitin (NG) | Project Brainstorm Meeting (Friday) | 1.5
| Administrative Tasks(Google docs Setup, Calendar Setup) | 2
| Literature review for Initial project Idea(Slack) | 1
Changed the initial project Idea from Slack to StackOverflow Analysis
Arturo (AR) | First Brainstorm Meeting | 1.5
| Articulation Work: Create a shared Repository and calendar | 2
| Literature Review for Initial Idea: Slack | 1
Breck (RBW) | Project Brainstorm Meeting (Friday) | 1.5
Tim (TB) | Project Brainstorm Meeting | 1.5
Alastair (AB) | Project Brainstorm Meeting (Friday) | 1.5

## Week 2
CSCW Project - Fall2015
Team: The High Fivers
CSCW Project - Fall2015
Week 2 (5th Oct – 9th October)
| Tasks | Hours Spent
Nitin (NG) | Meeting with Arturo (Thursday)[Literature Review Paper selection and Project Ideas discussion] | 2
| More research on related work for project | 2
| Meeting (Friday) [Tasks assignment, Final project discuss, Literature review Papers assignment to team member] | 1.5
| Literature Review on the assigned paper and write a summary | 6
Arturo (AR) | Meeting with Nitin: Discuss about Literature review and Project Ideas | 2
| Research for new Literature Review about our final idea: How to improve collaboration through Gamification in Stack Overflow? | 4
| Group meeting: Define final project idea, literature review papers to be assigned to team members. | 1.5
| Read research papers and write the work Related section. | 5
Breck (RBW) | Project Reading/Contributions to Proposal | 3
| Project Meeting | 1
Tim (TB) | Read Articles | 2
| Wrote the intro for Proposal | 2
Alastair (AB) | Read Articles | 2
| Wrote my part for Proposal | 2

## Week 3
CSCW Project - Fall2015
Team: The High Fivers
CSCW Project - Fall2015
Week 3 (12th Oct – 16th October)
| Tasks | Hours Spent
Nitin(NG) | Presentation Meeting (Tuesday) | 3
| Worked on Final proposal to add section for Methodology, Research questions, and Literature Review | 3
| Converted the proposal to the ACM format and proof reading of all the section | 3
Arturo (AR) | Presentation Meeting (Tuesday) | 3
| Read researches related to Gamification, StackOverflow and qualitative methods | 2
| Write the final proposal: Methodology, Research Questions and Literature Review | 3
| Revise all sections of the final proposal. Define the milestones, activities and roles | 3
Breck (RBW)
Tim (TB) | Presentation Meeting (Tuesday) | 3
Alastair (AB) | Presentation Meeting (Tuesday) | 3

## Week 4
CSCW Project - Fall2015
Team: The High Fivers
CSCW Project - Fall2015
Week 4 (19th Oct – 23rd October)
| Tasks | Hours Spent
Nitin (NG) | Survey question creation meeting | 3
| Friday meeting to complete survey questions and Milestone confirmation by team members | 2
| Interview Questions design with Arturo | 1
| Complete Ethics application, with the feedback | 3
| Improvised Log_Book for the team(Shared Excel file) | 1
Arturo (AR) | Fill out partially the Ethics application form | 3
| Create Google forms for survey and interview including some questions to facilitate meeting | 1
| Thursday survey question meeting | 3
| Friday meeting to complete survey questions and check activities and responsibilities by member on the project | 2
| Meeting with Nitin to include more interview questions | 1
| Modify Milestones according to feedback and including more detail activities | 1
Breck (RBW) | Thursday Meeting on Survey Questions (2015-10-22) | 2.5
| Email Template (2015-10-24) | 1
| StackOverflow/Github/Twitter API Research (2015-10-24) | 3
| Web Scraper Python Script (2015-10-24) | 4
Tim (TB) | Survey question creation meeting (Telecommute from class) | 2
| Updating log book | 1
| Friday meeting to complete survey questions and Milestone confirmation | 2
Alastair (AB) | Friday meeting to complete survey questions and Milestone confirmation by team members | 2
| Updated log book | 1
| Added Sql Queries | 3
| Updated Interview Questions | 1

## Week 5
CSCW Project - Fall2015
Team: The High Fivers
CSCW Project - Fall2015
Week 5 (26th Oct – 30th October)
| Tasks | Hours Spent
Nitin (NG) | Friday Meeting | 1
| Improve the survey Template based on pilot | 2
| Updated Milestones,Improving Email template for Survey, Sending emails to participants | 2
Arturo (AR)
Breck (RBW)
Tim (TB) | Improving my portion of the proposal based on feedback | 1.5
Alastair (AB)

## Week 6
CSCW Project - Fall2015
Team: The High Fivers
CSCW Project - Fall2015
Week 5 (26th Oct – 30th October)
| Tasks | Hours Spent
Nitin
Arturo (AR)
Breck (RBW)
Tim (TB)
Alastair (AB)